## Slide 1: Msc Project weekly progress update
Rahim

## Slide 2: Week 6 update (15th July 2021)
progress
Completed outcome variable
Success – IPO, Acquired or another round of funding in 5th to 7th years.
Features development – in progress
Write up – Introduction and Literature Review draft completed. Methodology ongoing.

## Slide 3: FEATURES SUMMARY
Features Categories | Not Started | In Progress | Completed
People/Founders | Board composition Advisory Team | Work experience | Founder’s Count Degree (Bachelor, Master, PhD, Ivy League, Top100 Uni, stem subject) Gender Diversity
Network |  | Event appearance | Social network presence (LinkedIn, Facebook, Twitter)
Innovation/Ecosystem | Kauffman Innovation Index Patent |  | Country Categories
Funding (Optional) | Funder’s reputation in previous round |  | 

## Slide 4: Week 6 update (15th July 2021)
Next week plan
Finalize features by 18th July
Develop and run model
Blocker/issues
Definition of early stage to define success? – currently up to 7 years. 0 to 4th year as warm up and 5th to 7th year as simulation.
Incomplete data? Change to 0 or drop?